## UserStories
Identifier | Priority | Description | Status | Estimate
1 | A | As a User I want this app available for Android in order to be available to Android users | In Progress | 4
2 | A | As a User I want this app available for iOS in order to be available to iOS users. | In Progress | 4
3 | A | As a User I want my app to receive transmitted data through Bluetooth in order to receive data from hardware. | DONE | 5
4 | A | As a User I want to have a 3d design of my housing in CAD in order to visualize it. | In Progress | 15+
5 | A | As a user I would like the app to handle what constitutes a "jump" | TODO | 10
5 | A | As a User I would like my housing 3d printed in order to prototype the wearable. | TODO | 2
6 | A | As a User I would like to see trials performed on my hardware in order to validate. | TODO | 5
7 | C | As a User I would like my app available on the Google Play Store | TODO | 1
8 | C | As a User I would like my app available on the Apple App store | TODO | 1
9 | A | As a User I would like my app to have a timer in order to time jump ropers | TODO | 3
10 | B | As a user I want to explore options for complete event data handling | TODO | 4
10 | A | As a User I want my jump count largely displayed on my app in order to be prominently visible | TODO | 2
11 | B | As a User I would like to integrate more personal wearables in order to facilitate more jump ropers. | TODO | 6/per device
12 | B | As a User I would like to control an entire jump rope event with one app in order to have more control over the event. | TODO | 8
13 | A | As a User I want the app button to control when the jumps are counted and stopped | TODO | 4
14 | A | As a User I want the app control button to also start a timer start/stop | TODO | 4
15 | C | As a User I want to control sound of the entire event from within the app | TODO | 4
16 | C | As a User I want the app to intake data of all jump devices to one location | TODO | 5
17 | D | As a user I want the jumper data logged into a user database for statistics | TODO | 8
18 | B | As a User I want the app to have a login for admin | TODO | 4
19 | B | As a user I want the app to have a login for jumper/users | TODO | 4
20 | D | As a User I would like to view my personal jump rope statistics on the user page | TODO | 6
21 | D | As a user I want to have a unique jumper ID associated with my wearable when I jump | TODO | 4
22 | D | As a user I want to have my unique jumper ID to coincide with my username | TODO | 4
23 | D | As a user I want my username to be able to be used at any event that uses this platform | TODO | 4

## AcceptanceCriteria
Identifier | Description | Status
2.1 | Given an android phone when a user wants the app, then it should be available for my platform. | TODO
2.2 | Given an android phone when a user wants the app, then it should be available for my platform. | TODO
2.3 | Given an app, when the user opens it, then it should be easily navigable. | Pass
2.4 | Given wearable hardware, when a jump occurs, then the hardware should register. | Pass
2.5 | Given wearable hardware, when a jump occurs, then the hardware should transmit data via Bluetooth | Pass
2.6 | Given valid data, when transmitted, then the app should receive data. | TODO
2.7 | Given hardware, when testing commences, then the hardware will be bundled | Pass
2.8 | Given hardware, when it’s used, then it should be protected | Pass
2.9 | Given a design for hardware housing, when design is complete, then it should be accepted. | TODO
2.1 | Given a design, when prototyping begins, then it should be 3d printed. | TODO
2.11 | Given a wearable hardware set, when physical testing commences, then testing should be done on children. | TODO
2.12 | Given a complete app, when the user needs to download, then it should be available on the Google Play store. | TODO
2.13 | Given a complete app, when the user needs to download, then it should be available on the Apple app store. | TODO
2.14 | Given a button for bluetooth, when pressed, then the app should connect to bluetooth hardware. | Pass
2.15 | Given a timer, when the user starts timer, then it should time jump ropers. | TODO
2.16 | Given an app display, when the user views the display, then the counter should be prominently displayed. | TODO
2.17 | Given a valid start/stop button, when the user presses button, then it should start/stop timer. | TODO
2.18 | Given a jump rope event, when there is more than one jumper, then there should be enough wearables to accommodate all of the jumpers. | TODO
2.19 | Given a single event, when controlling the event, then it should be controlled by one single app. | TODO
2.2 | Given hardware, when it needs to be worn, it should be able to be fashioned as such. | TODO

## Tasks
Story Identifier | Task Description | Status | Developer(s)
3 | Download required Ionic software/plugins on personal box | Complete | Catherine Henry, Shane McCandless
3 | Download Ionic Lab on personal box | Complete | Catherine Henry, Shane McCandless
3 | Download required Cordova Plugins on personal box | Complete | Catherine Henry, Shane McCandless
3 | Create basic Ionic App deployed to emulator | Complete | Catherine Henry, Shane McCandless
1 | Build Ionic app for android using Ionic Lab | ToDo | Catherine Henry
2 | Build Ionic app for iOS using Ionic Lab | ToDo | Shane McCandless
3 | Make a landing page with logo and clean color scheme using AngularJS | Complete | Catherine Henry
4 | Write a logic sequence within a method to detemine X-value coordinates and mathematically deduce when a jump has occurced. | Complete | Zach Goodspeed
5 | Integreate UART Service code into the hardware main setup method to establish bluetooth connection. | Complete | Zach Goodspeed
6 | Download plugins for Bluetooth compatible with Angular | Complete | Catherine Henry, Shane McCandless
6 | Implement plugins and create button to scan for available bluetooth devices | In Progress | Catherine Henry, Shane McCandless
6 | Connect to Adafruit via bluetooth | ToDo | Catherine Henry, Shane McCandless
6 | Receive transmitted data via bluetooth | ToDo | Catherine Henry, Shane McCandless
7 | Sew the adafruit components together using conductive thread | Complete | Zach Goodspeed
8 | Look into 3d, wood, other models to house wearable | Complete | Zach Goodspeed Catherine Henry Shane McCandless Afton Carlson
9 | Use CAD to make design for finished unit | In Progress | Zach Goodspeed
10 | Use school 3d printers to print model designed in CAD | ToDo | Shane McCandless Zachary Goodspeed
11 | Connect wearable to different people walking, jumping, running to make sure only counts with a proper jump. Test on kids and adults | ToDo | Shane McCandless Catherine Henry Afton Carlson Zach Goodspeed
12 | Look into how to get app on google play | ToDo | Catherine Henry
12 | Get app available on google play | ToDo | Catherine Henry
13 | Look into how to get app on apple store | ToDo | Shane McCandless
13 | Get app available on apple store | ToDo | Shane McCandless
14 | Make a button to select a bluetooth device | In Progress | Catherine Henry, Shane McCandless
15 | Look into timer options/plugins available | ToDo | Catherine Henry, Shane McCandless
15 | Implement timer into app and have a nice visual | ToDo | Catherine Henry, Shane McCandless
16 | Create label in app that show updated count large and clear (Maybe on it's own page?) | In Progress | Catherine Henry, Shane McCandless
17 | Create buttons to start and stop the timer. Consider having one button that updates to stop after clicked as start and vice versa | ToDo | Catherine Henry Shane McCandless
18 | Look into options for mass producing this wearable | ToDo | Zach Goodspeed Catherine Henry Shane McCandless Afton Carlson
18 | Proceed with selected option for mass production (more tasks to come as this one goes on) | ToDo | Zach Goodspeed Catherine Henry Shane McCandless Afton Carlson
19 | Complete an entire event with our app and wearable! | ToDo | Zach Goodspeed Catherine Henry Shane McCandless Afton Carlson
20 | Complete a sufficiently wearable housing and saudering of the adafruit to be wearable | ToDo | Zach Goodspeed Catherine Henry Shane McCandless Afton Carlson