## Tasks
Identifier | Story | Task | Owner | Estimate | Status
1.1 | 1 | Start base android platorm for app | Catherine | 2 | InProgress
2.1 | 2 | Start base iOS platform for app | Catherine | 2 | InProgress
3.1 | 3 | Build very open large landing paeg | Shane | 1 | Pass
3.2 | 3 | Create and insert logo | Shane | 1 | Pass
3.3 | 3 | Create buttons for timer and bluetooth | Shane | 1 | Pass
4.1 | 4 | Write method for reading accelerometer data | Zach | 1 | Pass
4.1 | 4 | Change method to look for x-value change in coordinates | Zach | 1 | Pass
4.2 | 4 | Test output to test screen, and jump with device | Zach | 1 | Pass
5.1 | 5 | Write UART service code for hardware side | Afton | 1 | Pass
5.2 | 5 | Integrate UART code into hardware loop method | Afton | 1 | Pass
5.3 | 5 | Test UART connection with handhelf device | Zach | 1 | Pass
6.1 | 6 | Write app side UART receive service | Shane | 2 | InProgress
7.1 | 7 | Sew main, bluetooth, and accelerometer together for temp. prototype | Afton | 1 | Pass
8.1 | 8 | Look into best course of action for housing | Afton | 2 | Pass
9.1 | 9 | Design 3D CAD housing for 3D printing | Zach | 5+ | InProgress
14.1 | 14 | Code functionality for bluetooth button | Catherine | 1 | Pass
14.2 | 14 | Create method for UART receive to see device | Catherine | 1 | Pass
17.1 | 17 | Design a start/stop button | Shane | 0.5 | Pass
17.2 | 17 | Code functionality for timer button to start counting the data sent from device as jumps | Shane | 0.5 | Pass
20.1 | 20 | Design strap style setup to clip device to for wearability | Zach, Catherine | 3 | Pass