## UserStories
Identifier | Priority | Description | Status | Estimate
1 | A | As a User I want this app available for Android in order to be available to Android users | In Progress | 4
2 | A | As a User I want this app available for iOS in order to be available to iOS users. | In Progress | 4
3 | A | As a User I want my app to receive transmitted data through Bluetooth in order to receive data from hardware. | In Progress | 5
4 | A | As a User I want to have a 3d design of my housing in CAD in order to visualize it. | In Progress | 15+
5 | A | As a user I would like the app to handle what constitutes a "jump" | TODO | 10
6 | A | As a User I would like my housing 3d printed in order to prototype the wearable. | TODO | 2
7 | A | As a User I would like to see trials performed on my hardware in order to validate. | TODO | 5
8 | C | As a User I would like my app available on the Google Play Store | TODO | 1
9 | C | As a User I would like my app available on the Apple App store | TODO | 1
10 | A | As a User I would like my app to have a timer in order to time jump ropers | TODO | 3
11 | B | As a user I want to explore options for complete event data handling | TODO | 4
12 | A | As a User I want my jump count largely displayed on my app in order to be prominently visible | TODO | 2
13 | B | As a User I would like to integrate more personal wearables in order to facilitate more jump ropers. | TODO | 6/per device
14 | B | As a User I would like to control an entire jump rope event with one app in order to have more control over the event. | TODO | 8
15 | A | As a User I want the app button to control when the jumps are counted and stopped | TODO | 4
16 | A | As a User I want the app control button to also start a timer start/stop | TODO | 4
17 | C | As a User I want to control sound of the entire event from within the app | TODO | 4
18 | C | As a User I want the app to intake data of all jump devices to one location | TODO | 5
19 | D | As a user I want the jumper data logged into a user database for statistics | TODO | 8
20 | B | As a User I want the app to have a login for admin | TODO | 4
21 | B | As a user I want the app to have a login for jumper/users | TODO | 4
22 | D | As a User I would like to view my personal jump rope statistics on the user page | TODO | 6
23 | D | As a user I want to have a unique jumper ID associated with my wearable when I jump | TODO | 4
24 | D | As a user I want to have my unique jumper ID to coincide with my username | TODO | 4
25 | D | As a user I want my username to be able to be used at any event that uses this platform | TODO | 4

## AcceptanceCriteria
Identifier | Description | Status
1.1 | Given an android phone when a user wants the app, then it should be available for my platform. | TODO
1.2 | Given an android phone when a user wants the app, then it should be available for my platform. | TODO
1.3 | Given an app, when the user opens it, then it should be easily navigable. | Pass
2.4 | Given wearable hardware, when a jump occurs, then the hardware should register. | Pass
2.5 | Given wearable hardware, when a jump occurs, then the hardware should transmit data via Bluetooth | Pass
2.6 | Given valid data, when transmitted, then the app should receive data. | TODO
2.7 | Given hardware, when testing commences, then the hardware will be bundled | Pass
2.8 | Given hardware, when it’s used, then it should be protected | Pass
2.9 | Given a design for hardware housing, when design is complete, then it should be accepted. | TODO
2.1 | Given a design, when prototyping begins, then it should be 3d printed. | TODO
2.11 | Given a wearable hardware set, when physical testing commences, then testing should be done on children. | TODO
2.12 | Given a complete app, when the user needs to download, then it should be available on the Google Play store. | TODO
2.13 | Given a complete app, when the user needs to download, then it should be available on the Apple app store. | TODO
2.14 | Given a button for bluetooth, when pressed, then the app should connect to bluetooth hardware. | Pass
2.15 | Given a timer, when the user starts timer, then it should time jump ropers. | TODO
2.16 | Given an app display, when the user views the display, then the counter should be prominently displayed. | TODO
2.17 | Given a valid start/stop button, when the user presses button, then it should start/stop timer. | TODO
2.18 | Given a jump rope event, when there is more than one jumper, then there should be enough wearables to accommodate all of the jumpers. | TODO
2.19 | Given a single event, when controlling the event, then it should be controlled by one single app. | TODO
2.2 | Given hardware, when it needs to be worn, it should be able to be fashioned as such. | TODO

## Tasks
Story Identifier | Task Description | Status | Developer(s)
1 | Build Ionic app for android using Ionic Lab | In Progress | Catherine Henry
2 | Build Ionic app for iOS using Ionic Lab | In Progress | Shane McCandless
3 | Design app side bluetooth protocol for communication | TODO | Zach Goodspeed
3 | Test logic and completeness of bluetooth protocol | TODO | Afton Carlson
4 | Design 3D housing in Solidworks 16 | In Progress | Zach Goodspeed
5 | Create algorithm to read bluetooth data and determine if there was an actual jump | TODO | Afton Carlson, Zach Goodspeed
5 | Print to app screen the count of jumps as it's incremented | In Progress | Catherine Henry, Shane McCandless
6 | Print out the CAD design of the hardware on Boise State's 3D printers | TODO | Zach Goodspeed
6 | Assemble the Adafruit Boards and battery within housing | TODO | Afton Carlson
6 | Test wearing the prototype | TODO | Afton Carlson, Zach Goodspeed
7 | Demonstrate prototype functionality to client | TODO | All
10 | Design button in Ionic and place onto app landing page | TODO | Catherine Henry
10 | Write a timer method for using the button | TODO | Shane McCandless
15 | Call method to start/stop or be called when timer button is pressed | TODO | Catherine Henry, Shane McCandless
15/16 | Test button functionality | TODO | Catherine Henry, Shane McCandless
15/16 | Test counting functionality within timer constraints | TODO | Catherine Henry
11 | Search ways to take multiple wearables and stream data to a single device. | TODO | Afton Carlson
12 | Design a readable count display | TODO | Shane McCandless
12 | Match the display to data being counted within the couting algorithm | TODO | Catherine Henry, Shane McCandless
13 | Order, print, and assemble more hardware wearables | TODO | Zach Goodspeed
14 | Implement timer into app and have a nice visual | TODO | Catherine Henry, Shane McCandless
16 | Call counting algorithm when timer button is pressed to start | TODO | Catherine Henry, Shane McCandless
16 | Stop counting algorithm when timer button is pressed to stop | TODO | Catherine Henry, Shane McCandless